## Sheet1
Task# | Date | Tasks | Constraints | Status
1 | 21Sep - 25th Sep | Core DS Environment Setup and Platform for UmaSankar (Anaconda , R Studio, MS SQL and GitHub Desktop) |  | In Progress
2 | 21Sep - 25th Sep | Research and Freeze on all relevant ML libraries
3 | 24th Sep | Design Document Baseline and Signoff ,Ver1.0
4 | 25th Sep - 4th oct | Proof of Concept Build ( Gasket Data) | (Completion of) Tasks 1, 2,3
- Sample Data Dictionary
-Basic Text processing
- Advanced Text processing
- Training model and Sample Supervised Classification *
-UI Prototype
5 | 4th Oct-5th Oct | First Demo Run / Gasket and produce the DQ report sample | 4
6 | 5th Oct - 5th Nov | Development and Testing, Full Data | 5
7 | 5th Nov - 8th Nov | ML Performance Testing with Testing Data | 6
8 | 8th Nov -16th Nov | Performance Tuning and Code Enhancements | 6,7
9 | 17th Nov -21st Nov | Second Demo Run /Regression Testing & Full Data Testing
10 | 21st Nov >…. | Further performance enhancement /tuning
11 | 23rd Nov | Version 1.0 Rollout
Key Milestones
| * | Dependent on DD/Text processing run